## Slide 1: Monthly status report
Project Atlas
Website relaunch & customer portal — progress, risks and next steps for March 2027.
REPORTING PERIOD · MAR 1 – MAR 31, 2027

## Slide 2: Mostly on track, one risk to watch
EXECUTIVE SUMMARY
Project Atlas — Status Report
02
OVERALL STATUS
At risk
Design and build are on schedule. The payment integration is two weeks behind and may push launch.
Done this month
Homepage and product pages shipped to staging; 41 of 57 tickets closed.
Watch
Payment provider sandbox access delayed — vendor escalation open.
Decision needed
Approve moving launch from Apr 28 to May 12, or cut saved carts from v1.

## Slide 3: Progress at a glance
KEY METRICS
Project Atlas — Status Report
03
Scope complete
72%
+14 pts vs last month
Tickets closed
41/57
9 closed this week
Spent of $240k
$184k
77% of budget used
Open risks
2
1 high, 1 medium
BURN-UP
Week 1
Week 12 · launch

## Slide 4: Where we are on the timeline
MILESTONES
Project Atlas — Status Report
04
Jan 15
Kickoff
Done
Feb 10
Design sign-off
Done
Mar 20
Staging build
Done
Apr 14
Payments live
At risk
Apr 28
Public launch
On track
May 30
Retro & handover
On track
Today: March 31 — staging complete, payments integration in progress.

## Slide 5: Status by team
WORKSTREAMS
Project Atlas — Status Report
05
WORKSTREAM | OWNER | PROGRESS | STATUS | NOTE
Design system | Priya N. | 100% | Done | Handed off to build
Front-end build | Marco B. | 85% | On track | Product pages in QA
Customer portal | Jess T. | 60% | On track | Orders + profile done
Payments | Omar K. | 35% | At risk | Waiting on sandbox access
Content & SEO | Hana L. | 70% | On track | 120 of 170 pages migrated
Analytics | Leo F. | 20% | Blocked | Needs consent banner first

## Slide 6: Spend is tracking slightly ahead of plan
BUDGET
Project Atlas — Status Report
06
Chart: 
| Jan | Feb | Mar | Apr | May
Planned ($k) | 40 | 95 | 150 | 205 | 240
Actual ($k) | 44 | 108 | 184
$184k
spent to date
$56k
remaining
+$34k
over plan at this point

## Slide 7: What could slow us down
RISKS & ISSUES
Project Atlas — Status Report
07
RISK | IMPACT | LIKELIHOOD | MITIGATION | OWNER
Payment sandbox delay | High | High | Escalated to vendor; mock API in parallel | Omar K.
Content migration slips | Medium | Medium | Two extra writers for 3 weeks | Hana L.
Consent banner legal review | Medium | Low | Use pre-approved template text | Leo F.
Load spikes at launch | High | Low | Load test on Apr 20; CDN rules ready | Marco B.

## Slide 8: Wins and blockers
THIS MONTH
✓ Wins
! Blockers
Staging site live with all product pages
Page speed score up from 61 to 94
Portal login + order history done
Accessibility audit: zero critical issues
Payment sandbox access (vendor)
Analytics waiting on consent banner
One front-end developer out for 2 weeks
Project Atlas — Status Report
08

## Slide 9: Plan for the next four weeks
NEXT STEPS
Project Atlas — Status Report
09
Apr 4
Finish payment integration against mock API
Omar K.
Apr 8
Ship consent banner and analytics
Leo F.
Apr 14
Content freeze — all pages migrated
Hana L.
Apr 20
Load test and security review
Marco B.
Apr 24
Go / no-go meeting with stakeholders
Jess T.

## Slide 10: Who to ask
CONTACTS
Jess Taylor
Marco Bianchi
Priya Nair
Omar Khalil
Project lead · jess@company.com
Engineering lead
Design lead
Payments & integrations
Project Atlas — Status Report
10

## Slide 11: Questions?
Next report: April 30, 2027
Project lead: jess@company.com